Timeline & Project Plan

Programme: Capacity Building & Training Grant – 30 -Month (12+3) for each round  Professional Diploma
Host Association: UKABCSContact (Grants): Programmes-Grants@ukabcs.co.uk

1) Introduction

This plan outlines the team structure, training schedule, milestones, reporting cadence, and end-of-grant outputs for the 12-month professional diploma in Drug Discovery & Computational Sciences. The programme strengthens institutional capacity through structured training (14 modules), supervised project work, and dissemination (poster + conference paper).

2) Team Composition & Roles

Each applying institution may register up to 5 teams. Each team consists of 10 researchers (Professors/Faculty, Postdocs, PhD/MSc students). Teams progress through the modules together and develop a unified research project.

2.1 Team Table (to be completed by the applicant)

| Team No. | Members per Team | Roles (mix required) | Notes |
| --- | --- | --- | --- |
| Team 1 | 10 | Professors, Postdocs, MSc/PhD Students | Max 5 teams per institution |
| Team 2 | 10 | Professors, Postdocs, MSc/PhD Students |  |
| Team 3 | 10 | Professors, Postdocs, MSc/PhD Students |  |
| Team 4 | 10 | Professors, Postdocs, MSc/PhD Students |  |
| Team 5 | 10 | Professors, Postdocs, MSc/PhD Students |  |

Roster to attach (per team): Full name, role, department, email, ORCID (if available).

3) Registration & On-Boarding Workflow

- Award → Lists: Institution emails team rosters (names, roles, emails) to grants@ukabcs.org and the executing company (CC the association).

- Platform Access: Executing company registers all participants on the training platform and confirms completion to the association.

- Orientation Week (Week 0): System walkthrough, accounts verification, policies, success criteria.

- Admin Fee Handling: One-time operational fee per researcher (Developed £100 / Developing £50). Waiver may be requested; decisions communicated in writing.

4) Training Modules & Learning Timeline

Orientation Week → 14 integrated modules → Poster (1 month) → Conference Paper (2 months).
After Modules 1 & 2, each team receives 3 weeks to develop and submit its Research Proposal that guides the rest of the diploma.

4.1 Modules Distribution

| Module | Duration | Topic |
| --- | --- | --- |
| 1 | 1 week | Introduction to Drug Discovery (Drug Design & CADD) |
| 2 | 2 weeks | Cheminformatics Databases & File Formats |
| Proposal Writing | 3 weeks | Team research proposal (after Modules 1–2) |
| 3 | 5 weeks | Protein Structure Prediction & Analysis |
| 4 | 2 weeks | Protein Alignment & Phylogenetics |
| 5 | 2 weeks | Gene Prediction & Protein–Protein Interaction |
| 6 | 4 weeks | ADME/Tox Prediction & Personalized Medicine |
| 7 | 2 weeks | Pharmacophore Modeling & Virtual Screening |
| 8 | 2 weeks | 3D-QSAR & Lead Optimization |
| 9 | 2 weeks | Structural Interaction Fingerprint Analysis |
| 10 | 3 weeks | Molecular Docking & Screening |
| 11 | 2 weeks | Quantum Calculations (DFT) |
| 12 | 5 weeks | Molecular Dynamics Simulation |
| 13 | 4 weeks | Google Colab Integration & Cloud Analysis |
| 14 | 3 weeks | Scientific Writing & Poster Presentation |

Note on pacing: Short modules (2 weeks) are intentionally compact. The executing company may sequence micro-assignments and clinics to maintain learning depth within compressed windows.

5) Project Timeline (Months 1–12) – Gantt-Style Overview

This overview balances sequential delivery with light overlaps for writing sprints. It respects the 12-month cap while preserving 1 month for Poster and 2 months for Paper through rolling manuscript development.

| Month | Primary Activities | Secondary / Overlaps (light) | Expected Outputs |
| --- | --- | --- | --- |
| 1 | Orientation + Module 1 + start Module 2 | Team formation, tool setup | Accounts active; M1 finished |
| 2 | Finish Module 2 → 3-week Proposal | Lit review clinics | Research Proposal submitted |
| 3 | Module 3 (wk 1–4) | Methods notes (draft) | M3 in progress |
| 4 | Finish Module 3 (wk 5) + Module 4 | Data capture framework | M3+M4 finished |
| 5 | Module 5 (2w) + start Module 6 (2w) | Results notebook v1 | M5 done; M6 partial |
| 6 | Finish Module 6 (2w) + Module 7 (2w) | Draft figures (early) | M6+M7 finished |
| 7 | Module 8 (2w) + Module 9 (2w) | Writing sprint #1 (Intro/Methods) | M8+M9 finished |
| 8 | Module 10 (3w) + start Module 11 (1w) | Data QC check | M10 finished; M11 partial |
| 9 | Finish Module 11 (1w) + Module 12 (3–4w) | Writing sprint #2 (Results outline) | M11 done; M12 in progress |
| 10 | Finish Module 12 (rem.) + start Module 13 | Figure drafting | M12 done; M13 partial |
| 11 | Finish Module 13 + Module 14 | Poster month (design & submission) | Poster submitted |
| 12 | Finish Module 14 → Conference Paper month #2 | Writing sprint #3 (final) | Paper submitted |

How the 2-month paper window fits: One month concentrated at the end (Month 12) + ~1 month equivalent accrued via Writing Sprints #1–2 during Months 7–10 (rolling manuscript development). This preserves total ≈2 months of writing time within the 12-month cap.

6) Deliverables & Acceptance Criteria

- Research Proposal (end of Month 2): Problem statement, aims, methods, data plan, risks, timeline (2–4 pages).

- Module Completion Evidence: Attendance, lab notebooks/notebooks in Colab, assignment submissions.

- Poster (Month 11): 1 scientific poster per team; template and brand guidelines provided; peer check by executing company.

- Conference Paper (Month 12): 1 paper per team formatted to conference/journal guidelines; similarity check ≤ 15%; all figures reproducible.

- Participation in UKABCS Conference: At least one presenter per team (online/offline per call guidance).

- Each institution must include in the final report a short sustainability plan outlining how the trained research teams will continue to apply and disseminate the acquired skills beyond the funding period.

7) Reporting & Monitoring (Quarterly)

All funded institutions must submit quarterly reports every 3 months to UKABCS.

Due: End of Months 3, 6, 9, 12
Contents (max 3–5 pages + annexes):

- Activities completed vs. timeline (Gantt progress).

- Attendance & completion stats per module.

- Interim outputs (notebooks, figures, partial results).

- Risks/issues & mitigations.

- “Reports should also include anonymised data on participation (e.g., gender balance, early-career researcher involvement) to ensure alignment with UKRI EDI principles.”

- Plan for next quarter.

Review & Feedback: UKABCS reviews within 15 working days and may request adjustments or targeted support. Late or missing reports may lead to participation suspension.

“Quarterly and final reports must include a short statement confirming compliance with institutional ethics approvals, safeguarding measures, and adherence to UKRI Good Research Conduct policies.”

8) Coordination & Communications

- Single Point of Contact (Institution): Name, title, email, phone.

- Team Leads: One lead per team (academic PI or delegated coordinator).

- Association Contact: grants@ukabcs.org

- Executing Company Contact: Provided in award letter.

- Status Emails:

  - Registration completion (company → association + institution)

  - Poster submission confirmation

  - Paper submission confirmation

9) Quality Assurance & Data Practices

- Reproducibility: Use version-controlled notebooks (e.g., Colab/Git).

- Data Management: Ensure lawful, ethical use of datasets; anonymize where needed; maintain metadata.

- Integrity: Plagiarism checks; proper citations; audit trails for analyses.

- Accessibility: Training materials hosted on the platform; recordings available per policy.

“All raw data, project records, and research outputs must be securely stored and retained for a minimum of seven (7) years after project completion. UKABCS and its authorised auditors reserve the right to request access for compliance verification, in line with UKRI standards.”

10) Risk Management (Typical)

| Risk | Likelihood/Impact | Mitigation |
| --- | --- | --- |
| Delays in platform access | Low/Med | Early roster submission; orientation checklist |
| Team turnover | Med/Med | Maintain 2 alternates/team; handover notes |
| Low attendance | Med/High | Automated nudges; office hours; escalation to PI |
| Slow progress on writing | Med/High | Scheduled writing sprints; editor clinics |
| Technical blockers | Low/Med | Helpdesk SLA; fallback tools |

11) Flexibility & Change Control

The executing company may adjust internal module sequencing or micro-schedules where needed provided that:

- The overall duration does not exceed 12 months.

- A maximum extension of 3 months may be granted by UKABCS in exceptional cases (written approval required).

- Any material changes (≥2 weeks shift) are communicated to the association and the institution’s contact.

12) Key Milestone Dates (External Call)

- Call Opening: 1 October 2025

- Call Closing: 15 November 2025 – 11:59 pm UK time

- Results Announcement: By December 2025

- Contracts Signed: By end of December 2025

- Grant Payments Initiated: By mid-January 2026
Note: Dates may shift if application volume is significantly higher than expected.