Timeline & Project Plan

UKABCS Conference Participation Support Grant

IJBTCS International Conference — December 2026

UK Association for Biotechnology and Computational Science (UKABCS) Document: Grant Timeline & Project Plan Version: 2026

Overview

The IJBTCS International Conference is scheduled for December 2026 (exact dates to be confirmed on the conference website). All grant applications — under both Track A and Track B — must be submitted with sufficient lead time to allow for full review and support activation before the conference date.

Deadline for Support: 20 September 2026

| Key Rule | Requirement |
| --- | --- |
| Deadline | 20 September 2026 |
| Review and decision timeline | Within 15 working days of a complete application |
| Grant Agreement signing | Within 7 working days of award notification |
| Support activation | Within 15 working days of signed Agreement |

Indicative Conference Calendar (December 2026)

Exact dates to be confirmed. All applicants should verify the official conference dates at ijbtcs.com before submitting.

| Milestone | Indicative Date |
| --- | --- |
| Abstract Submission Opens | To be confirmed — IJBTCS website |
| Abstract Submission Deadline | To be confirmed — IJBTCS website |
| Grant Application Deadline (latest) | 20 September 2026 |
| Grants Committee Review Period | October 2026 |
| Decision Notifications Sent | By end of October 2026 |
| Grant Agreements Signed | First week of November 2026 |
| Support Activated | By mid-November 2026 |
| Conference — Day 1 | December 2026 |
| Conference — Day 3 (End) | December 2026 |
| Post-Conference Report Due | Within 30 days of conference end |

Step-by-Step Timeline — Track A (Registration Fee Funding)

| Step | Action | Responsible | Timing |
| --- | --- | --- | --- |
| 1 | Applicant submits abstract to IJBTCS Conference | Applicant | Per conference abstract deadline |
| 2 | Applicant submits Track A application package by email | Applicant | At least 10 weeks before conference |
| 3 | UKABCS sends acknowledgement of receipt | UKABCS Admin | Within 5 working days |
| 4 | Administrative completeness check | UKABCS Admin | Within 5 working days of receipt |
| 5 | Grants Committee reviews and decides | Grants Committee | Within 15 working days of complete submission |
| 6 | Decision notification sent (Full / Partial / Rejected) | UKABCS | After committee review |
| 7 | Grant Agreement issued and signed (if funded) | Applicant + UKABCS | Within 7 working days of award |
| 8 | Registration fee support activated | UKABCS | Within 15 working days of signed Agreement |
| 9 | Applicant registers for conference | Applicant | Per conference registration deadline |
| 10 | Conference attendance (3 days) | Applicant | December 2026 |
| 11 | Post-conference report submitted | Applicant | Within 30 days of conference end |

Step-by-Step Timeline — Track B (Travel & Accommodation Funding)

| Step | Action | Responsible | Timing |
| --- | --- | --- | --- |
| 1 | Applicant submits abstract to IJBTCS Conference | Applicant | Per conference abstract deadline |
| 2 | Applicant gathers travel/accommodation cost estimates | Applicant | Before application submission |
| 3 | Applicant submits Track B application package by email | Applicant | At least 10 weeks before conference |
| 4 | UKABCS sends acknowledgement of receipt | UKABCS Admin | Within 5 working days |
| 5 | Administrative completeness check | UKABCS Admin | Within 5 working days of receipt |
| 6 | Grants Committee reviews budget, merit, and need | Grants Committee | Within 15 working days of complete submission |
| 7 | Decision notification sent (Full / Partial / Rejected) | UKABCS | After committee review |
| 8 | Grant Agreement issued and signed (if funded) | Applicant + UKABCS | Within 7 working days of award |
| 9 | Travel & accommodation support activated | UKABCS | Within 15 working days of signed Agreement |
| 10 | Applicant books travel and accommodation | Applicant | As early as possible after support activation |
| 11 | Conference attendance (3 days + extended programme if applicable) | Applicant | December 2026 |
| 12 | Post-conference report submitted | Applicant | Within 30 days of conference end |

Key Obligations Summary

| Obligation | Deadline |
| --- | --- |
| Acknowledge UKABCS in all presentations/materials | At conference |
| Attend the full conference programme | December 2026 |
| Notify UKABCS immediately if unable to attend | Before conference |
| Submit post-conference report | Within 30 days of conference end |

Contact

📧 Email: Programmes-Grants@ukabcs.co.uk 🌐 Conference Website: ijbtcs.com 🌐 UKABCS Website: www.ukabcs.co.uk/publications-conferences-support 📍 Address: 10 Portal Way, London W3 6RT, England, UK 📞 Phone: +44-7848180477

UKABCS — Advancing Biotechnology and Computational Science for a Better World Copyright © 2026 UKABCS. All rights reserved.