| FACILITY FROM THE REGIONAL TEACHER INITIATIVE FOR AFRICA |  |
| --- | --- |
| TERMS OF REFERENCE CALL FOR TENDERS TECHNICAL ASSISTANCE – TANZANIA Teachers’ professional development – Lower secondary schools vocational teachers’ pedagogical skills |  |
| CAP technical area | TEACHERS’ EDUCATION AND PROFESSIONAL DEVELOPMENT |
| CAP main action | ACTION 1: Development of a capacity building program for lower secondary schools’ vocational teachers (pedagogy) |
| Impacted indicators and objectives of the ESDP 2025/26-2029/30 | - 3.3.3 Strengthen the Teacher Continuous Professional Development program - Improve teachers’ competences and support for implementing secondary education curriculum - Increase the enrolment in vocational streams by 20.1% in 2030 (indirectly) |
| Estimated implementation period | July 2026 – October 2027 |
| Total estimated number of days | 126 days |
| Expected key deliverables | - Vocational teachers’ needs’ assessment report - Benchmark report on capacity building/induction programs for secondary vocational teachers - TCPD program for secondary vocational teachers - Methodological note for a TCPD program pilot (including MEAL tools) - Report on TCPD program pilot findings - Final version of the TCPD program Operationalisation plan of the TCPD program |
| National implementing partner (Unit in charge of interaction with the experts) | - MoEST : Office of the Commissioner of Education (Lead) Other partners involved: TIE, technical colleges |

# BACKGROUND

THE REGIONAL TEACHER INITIATIVE FOR AFRICA

The Regional Teacher Initiative for Africa (RTIA), a programme funded by the EU/EC via the Education section (G3) of DG INTPA aims to improve learning outcomes and the socio-emotional development of children in Africa, by having a more competent, motivated and inclusive teacher workforce in basic education.

The RTIA will especially seek to achieve the following outcomes over the next 6 years:

- Improve the governance, management, attractiveness, and gender balance of the teaching profession, with a strong focus on increased digitalization and innovation.

- Enhance the quality, relevance, and effectiveness of initial and continuous teacher professional development, notably through digital education, peer-to-peer learning approaches, and regional collaboration.

Within RTIA, the Facility will support teacher policy and improve teacher education and professional development systems by i) providing capacity building at country level through technical assistance, ii) promoting innovation and scaling of effective teaching solutions; iii) increasing the production and use of data and evidence, and iv) promoting the use of regional frameworks, evidence-based practices, and joint learning at regional level.

The Facility from RTIA will reach the above-mentioned objectives through 3 types of instruments or “windows”: i) a window to deliver technical assistance on teacher governance and teacher education and professional development based on the demand from eligible partner countries, ii) a window on testing and scaling effective programs for teacher education and professional development in the thematic areas of digital skills, gender, green skills, and pedagogical skills, including in the context of refugees and displaced population, iii) a research window to create new evidence and support the integration of evidence in the policy making process and in the design of teacher education and professional development programs.

In addition to these windows the Facility’s knowledge management and communication activities will further contribute to the sharing of knowledge, evidence, and best practices related to the overall Initiative outcomes.

The Facility is funded by the European Union and co-implemented by the Partnership formed by four-member state agencies: Expertise France for France, Enabel for Belgium, EDUFI for Finland and Estdev for Estonia. Expertise France has been designated the Coordinating Agency for this Partnership. With the Facility governance scheme serving as the Initiative's governance scheme, it is expected that the Partnership will work closely with UNESCO and AUC, in charge of the other 2 components of the EU Initiative.

The duration of the action is scheduled from 01.02.2024 to 31.01.2030 (6 years) with a budget of

92.000.000 EUR.

The call for expertise falls within the scope of Window 1 consisting in the provision of technical assistance (TA) aimed at supporting countries in specific thematic areas related to teacher policy and governance, as well as teacher training and professional development.

## WINDOW 1: DEMAND-DRIVEN TECHNICAL ASSISTANCE

The Technical Assistance Window is a mechanism activated at the request of eligible countries in sub-Saharan Africa to mobilize expertise in the design and implementation of public policies and capacity building in two areas: the governance of the teaching profession and the training and professional development of teachers.

The Technical Assistance Window supports countries by mobilizing experts to assist in the design and implementation of national reforms and policies related to teachers. Its aim is to strengthen education systems and build institutional capacity to improve teaching effectiveness. This includes fostering social dialogue with teacher representatives and identifying strategies to enhance the status and attractiveness of the teaching profession.

Within the framework of this Facility, the term ‘technical assistance’ refers to the mobilization of institutional or individual technical expertise, whether European or African.

In order to ensure the sustainability of the initiative beyond its implementation period, the Facility seeks to encourage the establishment of partnerships between European and African public institutions.

##### COUNTRY ACTION PLAN (CAP)

The technical assistance is provided within the framework of a Country Action Plan (CAP), jointly developed by the technical teams of the requesting Ministry of Education and the Facility. A CAP is a set of coherent technical assistance actions covering a period of between 12 and 24 months, leading to targeted changes in synergy with the country's education sector plan (ESP) and teacher-related policies, if these exist or are being developed.

A CAP is the result of a process that includes:

- An expression of interest and needs from the requesting sub-Saharan African country – submitted by the national authorities (with the Ministry of Education as the focal point channeling the country's needs) with the support of EU delegations and EU Member State agencies in the country, if necessary;

- An analysis of the expression of interests and needs based on teacher policy (where available), teacher sections of the education sector plan and the GPE compact (if available), as starting points for assessing the relevance, feasibility and sustainability of the needs and identifying appropriate technical assistance and capacity building measures;

- A series of consultations and local interactions with the Local Education Group (LEG), the EU delegation, and EU agencies in the country (if they have not been consulted previously), with the aim of prioritizing the most strategic actions of the CAP, ensuring consistency with ongoing national and international programs on teachers, and sustainability by taking into account available or future investment lines in the field of education in the country. The CAP aims to support and complement existing initiatives. High priority will be explicitly given to technical assistance actions that prepare for or are directly linked to teacher policy reform and/or substantial investments in the sector, from national or international resources (e.g. national budget for teacher salaries, national budget for initial and continuing teacher training, multilateral and bilateral investment programs, among others).

##### CAP ACTIVITIES

Each CAP includes a list of specific activities to be carried out by technical experts. The activities are defined in a set of specifications covering one or more activities included in the CAP list. Technical assistance is provided in the short and medium term and aims to achieve precisely defined results.

##### PARTNERS AND FOCAL POINTS

The main partners in the technical assistance window are the ministries of education of eligible partner countries in sub-Saharan Africa. They are the main focal points in the development of CAPs, which means that they identify needs and, in collaboration with the Facility team, design the CAP actions.

CAPs may include technical assistance actions that benefit other institutional actors such as teacher training institutes, universities (when they are responsible for teacher training in particular), inspections, decentralized services, as well as other ministries involved in responding to the needs identified in the CAP (Ministry of Finance, Ministry of Planning, Ministry of Higher Education, etc.). In addition, ministries of education have the option of involving other actors, such as trade unions and teachers' organizations, as beneficiaries of technical assistance and in activities related to teaching policy reforms and the revitalization of the teaching profession.

Where CAPs from different countries have similarities in their programs or activities, the Facility proposes to facilitate collaboration and exchanges between these countries, depending on their interest and availability.

## TANZANIA REQUEST FOR TECHNICAL ASSISTANCE

The Tanzanian request sent by the Ministry of Education, Sciences and Technology (MoEST) on December 16, 2025, included three technical areas, all related to teachers’ education and professional development.

- In-service teacher professional development training in technical and pedagogical for vocational secondary school teachers in Tanzania

- Development of a Bachelor’s Degree Program for vocational secondary school teachers in Tanzania.

- In-service teacher professional development training in foundational learning in primary education in Tanzania.

Before the first online technical call with the RTIA Facility team, the MoEST decided to prioritize and to keep only the areas 1 and 3.

The MoEST request was approved by the Facility on February 6, 2026.  In March 2026, an in-country mission with 3 experts from the Facility led to the co-development of a Country Action Plan (CAP) for Tanzania Mainland. Besides the two main activities on in-service teacher professional development already included in the request, a third complementary component was added, aiming at better equipping educators to support children’s transition from pre-primary to primary and from primary to secondary.

## BACKGROUND INFORMATION – MAJOR EDUCATION POLICY AND REFORMS STATUS IN TANZANIA

Tanzania became a lower-middle income country in 2020. It ranks 165 out of 193 countries in the Human Development Index (2023).  The population is very diverse, with more than 120 ethnic groups. The country counts 72 million inhabitants; almost 45% being under 15 years old.

According to UNICEF, 3.2 million children aged 7–17 are out of school, of which 1.2 million have never attended. The net secondary enrolment rate is only 27%.

The number of teachers in primary education reached 230 000 in 2024 according to the World Bank, for around 11,4 million pupils. The pupil-teacher ratio remains high (1:57) and this average number does not reflect classroom realities across the country, as in some areas for example, schools have more than 1000 students for 3 teachers. Despite the continuous efforts in teachers’ recruitment, the education system still suffers from teachers’ shortage, in particular in secondary education for science, mathematics and practical subjects.

In 2023, the Ministry of Education, Science and Technology launched a new education reform, with several major changes:

- the introduction of a competency-based curriculum;

- 10 years of compulsory education years (6 years primary and 4 years secondary);

- an education structure built on 1+6+4+2/3+3+, meaning one year of pre-primary education, six years of primary education (instead of 7 before), four years of secondary education, two years of advanced secondary or three years of technical education and a minimum of three years of higher education;

- the division of lower secondary education in two streams: the general education stream and the vocational education stream.

Diagnostic assessments in Standard 2 and 4 on reading, writing and arithmetic (3R) show that most of the learners don’t reach the required proficiency level.  To improve foundational teaching and learning, the ESDP 2025/26 to 2029/30 puts an emphasis on teachers’ continuous professional development in pre-primary and primary, with the objective of increasing foundational learning outcomes by 25% by 2030.

Adolescent birth rate remains very high in Tanzania at 123.4 per 1,000 births (UNDP, 2022).  In rural areas, 25% of teenagers have experienced pregnancy, which influences negatively the completion of their schooling. In TVET, socio-economic, cultural and institutional factors undermine girls’ enrolment, particularly in technical fields where female participation remains low due to cultural norms that discourage women from pursuing certain trades.

The implementation of the Education and training policy edition 2023 and the ESDP intends to be a response to concerns raised in Tanzania around education efficiency and relevance in terms of market’s needs, with graduated youth not able to find a job. As a result, the education reform in Tanzania intends to put in place a duo education system, offering theoretical and practical education simultaneously for education to better prepare young people for their integration into the labour market.

## LOGIC OF INTERVENTION

The Tanzania CAP is based on priorities identified in the Education Sector Development Plan (ESDP) 2025/26 to 2029/30. Given that the MoEST objective is to increase the enrolment in vocational streams by 20,1% in 2030, there is an urgent need to strengthen the vocational teachers in pedagogy (as many are professionals without a teaching background) and to work on the transition between primary and secondary through equipping primary school teachers with career guidance skills.

To increase transition between primary and secondary education, whether in general or in vocational streams, retention and participation of girls and boys in primary school is essential. This retention is currently undermined by many factors (including families’ economic resources), but also by insufficient learning outcomes that jeopardize children’s motivation and progress through the school system.  In primary education, results of diagnostic assessments in standard 2 focusing on reading, writing and arithmetic (3Rs), show that most learners do not reach the required proficiency levels. Despite the existence of remedial programs, there is a need to increase teaching and learning effectiveness, with a focus on foundational learning. The proposed intervention will aim at collaborating with teachers’ training colleges to improve teachers’ training programs on foundational learning for enhanced implementation in the classroom.

The Tanzania CAP intends to contribute to the ESDP objectives and education reform priorities by focusing on in-service teachers’ professional development, to enable 1- a smoother transition from pre-primary to primary and from primary to secondary; 2- enhanced capacities of teachers to deliver the competency-based curriculum, both for the improvement of foundational learning outcomes and for quality vocational and technical secondary education.

Even if transition is part of the two main areas identified in the request (1 and 3), it was decided to keep it as an independent work package, given that teachers involved in transition are teaching in different education levels (pre-primary, standard 1 & 2 primary, standard 6 primary and lower secondary vocational and technical stream). However, the activities related to transition will be carried out in line with the activities in the two other work packages.

As a result, the Tanzania CAP includes three areas of intervention, all under teachers’ professional development.

Below is the rationale for each technical area of the country action plan.

###### ACTION 1: teachers’ professional development

- Capacity building program for lower secondary schools’ vocational teachers (pedagogy)

The launch of the lower secondary technical and vocational stream has been piloted in a selection of secondary schools. However, there are not enough qualified technical and vocational teachers in the country; and the gaps will remain for several years, time for new teachers to finalize the pre-service training and to be recruited.

Currently, secondary schools are recruiting professionals to fill the gaps. These professionals are experts in their profession, but not trained as teachers. Despite the 2-week induction program, they are lacking pedagogical skills. The action therefore aims at strengthening teaching practices in the lower secondary technical and vocational stream, through a specific TCPD program.

The objective is to identify vocational teachers’ needs, strengths and gaps of the existing induction program, and to carry out a benchmark of secondary school vocational teachers’ professional development in Africa. Based on the results, a TCPD program will be co-designed and piloted, before national implementation. This CAP work package will be implemented with the Tanzania Institute for Education and the Teachers’ training colleges.

###### ACTION 2: transition

- Development of guidelines and training packages for in-service teachers to support students’ transition to primary and to secondary

This action on transition was added for the sake of clarity but is fully aligned with the two other CAP actions.

To enhance transition from primary to lower secondary, in the context of the newly launched vocational and technical stream, there is a need to equip primary school teachers with career guidance skills. The main objective is to develop guidelines for teachers and head teachers in primary schools, for them to be able to orientate children and their families on secondary education opportunities.

To support a smoother transition from pre-primary to primary, it is essential to enhance teachers’ capacities of both education levels. Guidelines on school readiness will aim at equipping pre-primary teachers to better prepare children for primary. As most of the pre-primary and primary classes are in the same school premises, the focus will be on collaboration and sharing of experiences between teachers. The co-development of packages on play-based pedagogy for Communities of Learning in schools intends for teachers in pre-primary and primary to share and implement similar teaching practices aiming at enhancing children’s motivation and leaning, across pre-primary, standard 1 and standard 2, with a focus on foundational learning.

###### ACTION 3: teachers’ professional development

- Review and update of teacher training colleges’ programs to enhance implementation of foundational learning teaching practices in the classroom

Despite the teaching and learning materials developed, the investment of partners in foundational learning and teachers’ continuous professional development programs delivered by the teacher training colleges, the uptake and implementation of teaching practices remain insufficient to lead to improved learning outcomes. The first activities will be to do an assessment of the TCPD program on foundational learning and teachers’ remaining needs, and to carry out a benchmark of innovative and promising practices in Africa to enhance foundational learning outcomes. Based on the results, a strategy will be co-developed to strengthen the TCPD program. This strategy might result in the update / development of modules, the introduction of innovative approaches, and/or the update/development of monitoring tools.

The Tanzania CAP, despite targeting at the same time pre-primary, primary and lower secondary education, is quite coherent, with a focus on students’ progress across the education system. Foundational learning is at the essence of this progress, and it is important to note that the orientation of children at the end of primary is still heavily focused on their performance. It is essential at the same time to enhance learning outcomes in primary to support retention and transition to secondary, but also to ensure that quality education is delivered in lower education vocational and technical stream for this stream to be valued, and not be a compulsory or default choice for struggling children.

# SCOPE OF WORK – CAP ACTION 1

In this context, Expertise France is recruiting a consulting firm to implement this action.

The service covered by this contract corresponds to Action 1 of the Tanzania Mainland’s CAP.

## OVERVIEW

| Technical areas of expertise | Action description / Work package | Activities |
| --- | --- | --- |
| - Teachers’ professional development Lower secondary school vocational teachers’ pedagogical skills | - Development of a capacity building program for lower secondary schools’ vocational teachers (pedagogy) | - Conduct vocational teachers’ needs’ assessment (including review of induction program) - Carry out a benchmark on capacity building/induction programs for secondary vocational teachers - Design a TCPD program for secondary vocational teachers, including monitoring tools - Design a pilot, including ToT, follow-up and evaluation, of the TCPD program - Based on the pilot results, finalize the TCPD program, including an operationalization plan |

## OBJECTIVES OF THE ACTION 1

##### GENERAL OBJECTIVES

Enhance the quality of teaching practices in the newly launched lower secondary technical and vocational stream in Tanzania Mainland, through the implementation of a needs-based TCPD program

##### SPECIFIC OBJECTIVES

- Develop a TCPD program for lower secondary technical and vocational teachers, based on a needs-assessment and best practices in Africa

- Test, adjust and validate the TCPD program through the implementation of a pilot

- Design a realistic national implementation plan for the TCPD program developed, using MoEST existing resources and platforms.

## IMPLEMENTING NATIONAL PARTNERS

The Ministry of Education, Science and Technology (MoEST) who sent the request, is the main implementing partner and will be involved in all the CAP’s components. The Office of the Commissioner for Education who sent the request is also leading the CAP implementation.

The Tanzania Institute of Education (TIE) is a key partner to involve, as they are in charge of curricula development, capacity building of teachers and quality insurance.

The Technical Colleges will be involved for their technical expertise in technical and vocational education.

Finally, it is essential to involve the Local Education Group (LEG) to share information with education partners, and ensure that the CAP activities are not duplicating existing efforts, but rather complementing partners’ activities in Tanzania Mainland.

## APPROACH AND METHODOLOGY

The general approach and methodology described below are indicative and non-exclusive. The methodology used must be developed in the application file.

##### GENERAL APPROACH

The team of experts provided by the consulting firm will work closely with the representatives of the MoEST. A participatory approach is essential, to ensure that the deliverables  proposed are in line with their needs. The person leading this activity together with the technical team will be the ones guiding the process, identifying and involving relevant stakeholders, and taking responsibility for the validation processes.

The team of experts will also need to liaise with the European Union Delegation in Dar es Salaam for sharing information and better anchoring technical assistance in existing and future initiatives.

##### METHODOLOGY

The implementation of Action 1 of the CAP Tanzania requires the team of experts recruited to:

- Familiarize themselves with the main policy documents of the Tanzania Mainland education system (Tanzania education and training policy, 2023 edition; the ESDP 2025/26-2029/30; MEWAKA – National Teacher Development reform; the Partnership Compact; etc.)

- Participate in a scoping meeting with the focal points of the MoEST and the Facility. Following this meeting, the lead expert will propose a brief note describing the work to be carried out, including the methodology and an updated timetable, taking into account logistical and security constraints. This note will describe in detail the strategy implemented to carry out the various activities.

- Liaise regularly with MoEST representatives and the core technical group established for the co-development of the TCPD program.

- Co-facilitate working sessions with the core technical group through a participatory approach so that partners and key stakeholders are fully involved in the development process.

- Ensure buy-in and ownership of the process and deliverables by the core technical group and other education stakeholders, through a consultative approach and interim validations.

- Collect data on the methodology and deliverables produced: feedback from experts, participant evaluations and feedback from the core technical group.

##### COORDINATION

Throughout the mission, the lead expert (who will represent the team of experts, see section 3) is expected to hold technical meetings with the technical lead in Education (TLE) responsible for monitoring the implementation of the Facility's Tanzania CAP and the Education Officer (EO). The frequency of these meetings will be defined at the start of the mission.

## DELIVERABLES

Deliverables are validated by the MoEST and the RTIA Facility.

The main deliverables for action 1 are:

1.1.1 Vocational teachers’ needs’ assessment (including review of induction program)

Deliverable 1: Methodological note

This note will present the proposed methodology for carrying out the assessment, including desk review, sample of participants, proposed timeframe, and tools to be used for focus groups and/or interviews.

Deliverable 2: PP presentation of the findings to the core technical group

This presentation will enable the core technical group to provide inputs to fine-tune the findings and for the recommendations to be in the report.

Deliverable 3: Assessment report

The report includes an analysis leading to key findings and recommendations for the development of the TCPD program.

1.1.2 Benchmark on capacity building/induction programs for secondary vocational teachers

Deliverable 1: Benchmark findings’ report

The report includes a presentation of TCPD programs/ approaches for vocational teachers in Africa and recommendations for their relevance and potential adaptation to the Tanzanian context.

Note: it is recommended to carry out the assessment and the benchmark simultaneously and present the results in one report (2 parts) with recommendations taking into account the results of the assessment and the findings of the benchmark.

1.1.3 TCPD program for secondary vocational teachers, including monitoring tools

Deliverable 1: Roadmap for the design of the TCPD program

The roadmap is a note presenting the proposed process, participants, timeframe, structure, contents, validation steps etc. for the development of the TCPD program.

Deliverable 2: TCPD program and modules

Based on the agreed format/ structure/ contents, this deliverable is the first version of the TCPD program, including training pathways, stages and modules. It is essential for this deliverable to align with the existing induction program for enhanced complementary.

Deliverable 3: Monitoring and evaluation tools

The M&E tools will enable to monitor the implementation of the TCPD, and to measure the impact of the TCPD program on teachers’ capacities and teaching practices.

1.1.4 Pilot, including ToT, follow-up and evaluation, of the TCPD program

Deliverable 1: Pilot design (methodological note)

The note will present the methodology for a pilot of the TCPD program, including sample of schools/ teachers, selection of contents piloted, timeframe, and pilot monitoring/ evaluation tools

Deliverable 2: ToT for pilot implementation (design/ report)

This deliverable is divided in two: 1- module(s) for trainers of trainers who will conduct teachers’ training for the pilot, provide coaching and guidance in the classroom for these trained teachers, and evaluate progress in trained teachers’ performance. 2- ToT report including participants’ feedback.

Deliverable 3:  Pilot findings report

The report will compile the pilot findings and include recommendations for potential adjustments of the TCPD program.

1.1.5 Final version and operationalization plan of the TCPD program

Deliverable 1: Final TCPD program

The TCPD program will be adjusted based on the pilot findings. This deliverable is the final version, validated by the core technical group, of the TCPD program.

Deliverable 2: TCPD program operationalization plan

The operationalization will include roles and responsibilities, communication, steps for capacity building of trainers, and timeframe for the implementation of the TCPD program.

## ROLES AND RESPONSIBILITIES

###### The MoEST is responsible for:

    - Providing all the documentation required for the desk review and the preparation of the field work if any

    - Facilitating the organization of meetings and the involvement of relevant stakeholders (in-person and remotely) ensuring co-development of deliverables

    - Commenting on and approving deliverables

    - Sharing deliverables with key stakeholders

    - Ensuring that deliverables are taken on board by the national education authorities

    - Facilitating the validation process by the national authorities when necessary.

###### The RTIA Facility is responsible for:

    - Contracting and facilitating the integration of the team of experts by providing all available documents and resources

    - Supporting and monitoring the team of experts’ work from start to finish

    - Acting as the team of experts’ main resource person

    - Ensuring quality control of deliverables in collaboration with the MoEST focal points

    - Acknowledging final validation of deliverables by all parties

    - Evaluating the team of experts’ overall performance under this mandate.

###### The team of experts represented by the lead expert, are responsible for:

    - Reviewing and commenting on these Terms of Reference (ToR)

    - Ensuring that all deliverables comply with the ToR and the guidelines formulated during the scoping meeting, in accordance with the agreed timetable

    - Implementing all stages of the validated methodology through a participatory approach ensuring co-development of deliverables

    - Compiling and submitting the final report in a timely manner

    - Ensuring that relevant education stakeholders are consulted throughout the mission

    - Organizing /co-organizing consultations with technical and financial partners and national stakeholders working in the education sector

    - Behaving with the highest levels of personal integrity and committing to the required standards of good conduct

    - Submitting data relating to contractual services, RTIA monitoring and evaluation and quality assurance requirements, in particular by collecting attendance sheets, participating in the consultants’ satisfaction survey, and sharing information from the participants’ feedback survey with the RTIA.

    - Immediately reporting to the Facility any difficulties that could hinder the progress and achievement of the mission's objectives.

## LOGISTICS

All logistical aspects related to the implementation of the activities including missions, must be integrated in the technical and financial proposal and will be under the responsibility of the contractor.

Given the nature of the assignment, the experts will mainly be operating in regions classified as ‘yellow’ on the France Diplomatie scale, which means that travel is not discouraged, but heightened vigilance is advised: https://www.diplomatie.gouv.fr/fr/information-par-pays/tanzanie/conseils-aux-voyageurs-securite.

##### SECURITY

Subject to the provisions set out in the contract attached to the call for tenders, the Consulting firm is solely responsible for the safety of the persons and property it mobilizes for the performance of this contract and shall take all necessary measures in this regard. It undertakes to ensure that all its employees and subcontractors comply with the safety instructions it issues at all times. In the event of an incident and/or direct or indirect breach of the safety of persons mobilized directly or indirectly by the Contractor or its equipment, Expertise France shall not be held liable in any way whatsoever.

## TIMETABLE

| Activities | Estimated timeframe (end dates) |
| --- | --- |
| Vocational teachers’ needs’ assessment | August 2026 |
| Benchmark on capacity building/ induction programs for secondary vocational teachers | August 2026 |
| TCPD program for secondary vocational teachers, including monitoring tools | January 2027 |
| Pilot design including ToT | February 2027 |
| Monitoring of pilot implementation | June 2027 |
| Finalization of the TCPD program and operationalization plan | September 2027 |

#### The timetable will be finalized and approved in the inception report.

# EXPERTS’ PROFILES

Expertise France is recruiting a consulting firm that will provide a technical assistance team composed of several experts, in order to carry out the activities detailed above.

The team should include international and national experts. The international experts should be willing to travel to Tanzania. A gender-balanced team is an added value.

The proposed experts may not be members of the civil service, unless they are regularly placed on leave or seconded at the time of their assignment. In this case, proof from their original administration must be included with the application. The proposed experts may not have participated in the development of the CAP and of these Terms of reference.

DESIRED PROFILES

Lead expert:

###### Academic qualification:

Advanced degree in education

###### General work experience:

- Minimum of 10 years of experience in teachers’ education and professional development – in particular for the design of CPD programs for non-qualified teachers and/or technical and vocational teachers

###### Specific work experience:

- Experience in/ knowledge of developing or updating and delivering in-service teachers’ training programs

- Demonstrated expertise in pedagogy, including learner-centred teaching approaches

- Proven knowledge and experience of education policies and systems in Eastern Africa

###### Language Proficiency:

- Excellent proficiency in English (both written and spoken);

- Swahili proficiency is an asset

###### Interpersonal and soft skills and experience

- Ability to work in a team and communicate effectively with various stakeholders

- Experience in technical and political dialogue, with an aptitude for navigating complex institutional contexts

- Proven expertise in applying participatory and interactive approaches

###### Additional assets

- Previous experience working in Tanzania

- Familiarity with the education context and policies of Tanzania

Team of experts:

- In-depth knowledge of education policies and context in Tanzania

- In-depth knowledge of secondary education challenges in Tanzania (including gender issues)

- Experience in secondary teachers’ and TVET teachers’ professional development

- Expertise in gender in education (gender responsive pedagogy; orientation of girls and boys etc.)

- In depth knowledge of gender issues in technical and vocational education

- Experience in approaches and methodology for capacity building of non-qualified teachers

- Experience in induction programme development and articulation with in-service teacher training

- Experience in developing contents for and facilitating training of trainers

- Expertise in coordination, facilitation and mediation

The consulting firm is free to propose as many experts as it wishes. Preferably, the consulting firm will propose experts who are proficient in English and Swahili; with a mix of international and national experts for the different areas of expertise

# APPLICATION SUBMISSION

Interested candidates are requested to submit a technical offer and a financial proposal in response to these Terms of Reference. All the procedures for submitting tenders are set out in the document “Tender rules”.