## Slide 1: Activity networks and precedence tables
8H
Notes: 1-2, 4-5, 7-11

## Slide 3
8H Precedence Tables + Networks.
immediate predecessor: (IP)
an activity that must be completed before another activity can begin
they are displayed in precedence tables.
precedence tables:
shows activities and IP's
info is used to draw networks
activity networks no longer label vertices but instead label edges
start/finish vertices get labelled.
Example 1: draw an activity network from the precedence table
dummy activities:
required if two activities share SOME but NOT ALL IP's
begins @ the shared IP
ends @ the start of the activity that has additional IP's
drawn as a dotted line, and labelled 'd'.
Example 2:
example 3:
example 4:
activity | IP
A | —
B | A
C | A
D | A
E | B
F | C
G | D
H | E, F, G
it comes off start
all come off A.
MERGE TOGETHER
H is not an IP ∴ attaches to "Finish"
activity | IP
A | —
B | —
C | A
D | A
E | C, D
F | C
G | E, F
MERGE TOGETHER
comes off start
share C but not D ∴ they share some but not all IPs!
C was shared
ends @ start of E
End of B  start of D & E
End of C  start of F & G
End of G  start of J
Notes: Board notes

## Slide 4: Drawing activity networks from precedence tables
When activity A must be completed before activity B can begin, activity A is called an immediate predecessor of activity B.
A table containing the activities of a project, and their immediate predecessors, is called a precedence table.

## Slide 5: Drawing activity networks from precedence tables
An activity network can be drawn from a precedence table. Activity networks have edges representing activities. The vertices are not labelled, other than the start and finish vertices.

## Slide 6: Drawing activity networks from precedence tables
Activities A and B have no immediate predecessors.
These activities can start immediately and can be completed at the same time.

## Slide 7: Drawing activity networks from precedence tables
Activities A and B have no immediate predecessors.
These activities can start immediately and can be completed at the same time.

## Slide 8: Drawing activity networks from precedence tables
Activity E has immediate predecessor activity B so it will follows immediately after activity B.
Activity G has immediate predecessor activity F and activity E and so it must follow immediately after both of these activities.
Activity G is not an immediate predecessor for any activity and so the project is finished after this activity is complete.

## Slide 9: Drawing activity networks from precedence tables

## Slide 10: Drawing an activity network from a precedence table.
H is not an immediate predecessor for any other activity so it will lead to the finish of the project.
H has immediate predecessors E, F and G and so these three activities will lead into activity H.

## Slide 11: Drawing an activity network from a precedence table.
Activity D is an immediate predecessor of activity G and has immediate predecessor activity A. There will be a path through activity A, activity D and then activity G.
Activity C is an immediate predecessor of activity F and has immediate predecessor activity A. There will be a path through activity A, activity C and then activity F.

## Slide 12: Drawing an activity network from a precedence table.
Activity B is an immediate predecessor of activity E and has immediate predecessor activity A. There will be a path through activity A, activity B and then activity E.
Activity A has no immediate predecessors, so it is the start of the project.

## Slide 13: Sketching activity networks
Activities that have no immediate predecessors follow from the start vertex.
Activities that are not immediate predecessors for other activities lead to the finish vertex.
For every other activity, look for:
which activities for which it is an immediate predecessor
which activities it has as immediate predecessors.
Construct the activity network from this information.

## Slide 14: Dummy activities
A dummy activity is required if two activities share some, but not all, of their immediate predecessors.
A dummy activity will be required from the end of each shared immediate predecessor to the start of the activity that has additional immediate predecessors.
Dummy activities are represented in the activity network using dotted lines.

## Slide 15: Dummy activities

## Slide 16: Using a dummy activity in an activity network

## Slide 17: Creating a precedence table from an activity network
Activity | Immediate predecessors
A | —
B | A
C | A
D | B
E | C
F | C, D
G | D, C
H | F, E
I | G
J | H, G